## research_log
Date | Task
2026-04-10 | Meeting 0. Preliminary discussion with the supervisor on the research direction. Self-proposed topic: oil-price forecasting using spatial and shipping indicators.
2026-04-29 | Ethics review approved.
2026-05-06 | Meeting 1. Confirmed the dissertation direction as oil-price forecasting with spatial indicators. Discussed the difficulty of obtaining open shipping data, agreed to compile a dataset inventory, and planned an initial literature review.
2026-05-22 | Collected literature, ranked and classified it, and read it by category and importance. Completed the first blocks of the dataset inventory from the literature (market and financial data; official reports). Dropped paid ICE/CME sources and monthly STEO from the near-term design.
2026-05-25 | Selected variables from the literature. Bulk data acquisition and first pipelines: EIA, GDELT, OGIM/GOGET, PortWatch, GFW, EMODnet, and Sentinel-2/VIIRS for eight oil-infrastructure sites. Adopted a Friday-ending weekly calendar.
2026-05-27 | Meeting 2. Reviewed the dataset inventory. Agreed to reframe the question as whether remote sensing and shipping improve on financial data alone; to use a progressive four-model comparison (finance; finance + remote sensing; finance + shipping; all three); to drop text data from the main design; and to select a small, literature-justified variable set rather than adding further features.
2026-06-01 | Rewrote the research plan after Meeting 2: narrowed the question, adopted the four-model comparison, and dropped text data.
2026-06-05 | Began a structured literature review and selected finance, remote-sensing and shipping variable subsets from the literature. Built the first modelling pipeline.
2026-06-16 | Completed the finance-variable literature set and a first end-to-end modelling pipeline. Preliminary results showed a strong persistence benchmark, class imbalance on direction, and overfitting in deep models trained on price levels.
2026-06-17 | Meeting 3. Reviewed the first model results. Agreed to add a no-change Model 0 (next week's price equals this week's price), to compare all models on a common 2019–2026 window with a four-week lag, to document every variable, to simplify remote-sensing features, and to begin a thematic literature review.
2026-06-22 | Rebuilt a leakage-safe weekly feature matrix with publication lags and as-of remote-sensing alignment. Narrowed the sole target to next-week Brent price, trained on log return, and implemented Model 0.
2026-06-30 | Locked the contribution as application, integration and systematic comparison of representation-level versus flat fusion, not a new fusion operator. Completed Flat Model 0–Model 4 (Ridge and XGBoost) under a common expanding-window protocol.
2026-07-03 | Streamlined the finance block from the literature; built the 17-node shipping graph; ran modality-aware Deep models (finance TCN, frozen Prithvi remote-sensing encoder, shipping GAT, gated fusion). First evidence that structured shipping encoding can improve on flat fusion, though beating Model 0 remained difficult.
2026-07-04 | Started writing the literature review.
2026-07-08 | Meeting 4. Reviewed Flat and Deep results against Model 0. Agreed to stop major model redesign, keep Model 0 central, and present three result blocks (Flat versus Model 0; Deep versus Model 0; Flat versus Deep). Interpretability was restricted to models that beat Model 0.
2026-07-15 | Finished Chapters 1–2 and drafted the dissertation outline.
2026-07-16 | Received written feedback from Beatrice Taylor on structure and the literature review.
2026-07-20 | Revised Chapter 2 from the feedback, adjusted the structure, and continued writing Chapter 3.
2026-07-29 | Meeting 5. Last formal meeting before submission. Discussed sentence-level clarity; policy as broader geopolitical and trade context rather than one named statute; a world map of monitoring sites and chokepoints as the study-area figure; the balance between a readable narrative and a replicable method; and the Flat/Deep remote-sensing mismatch, which should be stated in the text.
2026-08-01 | Completed the first full draft.
2026-08-03 | Received written comments from Beatrice Taylor on narrative, methods clarity and presentation.
2026-08-11 | Revised the full draft; rebuilt the figure set (study-site map, worked example, RMSE comparisons, SHAP map and heatmap); aligned Bookdown numbering and Harvard references.
2026-08-17 | Finalised remaining figures.